## ADMIN
SL.NO | MODULES | TASKS | SUB-TASKS | MODIFICATION | ASSIGN | Effort min's | Start Date | End Date | STATUS | REMARKS
1 | Login | GUI/SERVER/DB |  |  | Kamali | 260 min | 2024-12-27 | 2024-12-27 | Done
1.1 | Login | GUI Creation |  |  | Kamali | 75min | 2024-12-27 | 2024-12-27 | Done
1.1.1 | Login |  | Building user interface |  | Kamali | 30 min | 2024-12-27 | 2024-12-27 | Done
1.1.2 | Login |  | Client-side Validations |  | Kamali | 45min | 2024-12-27 | 2024-12-27 | Done
1.1.3 | Login |  | Rest API integration |  | Kamali | 45min | 2024-12-27 | 2024-12-27 | Done
1.1.4 | Login |  | Unit Testing |  | Kamali | 40min | 2024-12-27 | 2024-12-27 | Done
1.2 | Login | Server |  |  | Sujata | 45min | 2024-12-27 | 2024-12-27 | Done
1.2.1 | Login |  | Server-side validation |  | Sujata | 50min | 2024-12-27 | 2024-12-27 | Done
1.2.2 | Login |  | Verify/Confirm login credentials |  | Sujata | 30min | 2024-12-27 | 2024-12-27 | Done
1.2.3 | Login |  | Unit Testing |  | Sujata | 20min | 2024-12-27 | 2024-12-27 | Done
1.3 | Login | Database |  |  | Sujata | 40min | 2024-12-27 | 2024-12-27 | Done
1.3.1 | Login |  | Table creation |  | Sujata | 30min | 2024-12-27 | 2024-12-27 | Done
2 | Register | GUI/SERVER/DB |  |  | Kamali | 235 min | 2024-12-27 | 2024-12-27 | Done
2.1 | Register | GUI Creation |  |  | Kamali | 75min | 2024-12-27 | 2024-12-27 | Done
2.1.1 | Register |  | Building user interface |  | Kamali | 30 min | 2024-12-27 | 2024-12-27 | Done
2.1.2 | Register |  | Client-side Validations |  | Kamali | 45 min | 2024-12-27 | 2024-12-27 | Done
2.1.3 | Register |  | Rest API integration |  | Kamali | 45 min | 2024-12-27 | 2024-12-27 | Done
2.1.4 | Register |  | Unit Testing |  | Kamali | 40 min | 2024-12-27 | 2024-12-27 | Done
2.2 | Register | Server |  |  | Sujata | 40min | 2024-12-27 | 2024-12-27 | Done
2.2.1 | Register |  | Server-side validation |  | Sujata | 25min | 2024-12-27 | 2024-12-27 | Done
2.2.2 | Register |  | Verify/Confirm Registration credentials |  | Sujata | 30min | 2024-12-27 | 2024-12-27 | Done
2.2.3 | Register |  | Unit Testing |  | Sujata | 20min | 2024-12-27 | 2024-12-27 | Done
2.3 | Register | Database |  |  | Sujata | 30min | 2024-12-27 | 2024-12-27 | Done
2.3.1 | Register |  | Table creation |  | Sujata | 30min | 2024-12-27 | 2024-12-27 | Done
3 | Components | GUI/SERVER/DB |  |  | Kamali | 195 min | 2024-12-28 | 2024-12-28 | Done
3.1 | Components | GUI Creation |  |  | Kamali | 75 min | 2024-12-28 | 2024-12-28 | Done
3.1.1 | Components |  | Header |  | Kamali | 45min | 2024-12-28 | 2024-12-28 | Done
3.1.2 | Components |  | Sidebar |  | Kamali | 45 min | 2024-12-28 | 2024-12-28 | Done
3.1.3 | Components |  | Footer |  | Kamali | 30 min | 2024-12-28 | 2024-12-28 | Done
4 | Category | GUI/SERVER/DB |  |  | Kamali | 535 min | 2024-12-28 | 2024-12-28 | Done
4.1 | Category | GUI Creation |  |  | Kamali | 90 min | 2024-12-28 | 2024-12-30 | Done
4.1.1 | Category | Main Category | View main category |  | Kamali | 30 min | 2024-12-28 | 2024-12-28 | Done
4.1.2 | Category |  | Add main category |  | Kamali | 45 min | 2024-12-28 | 2024-12-28 | Done
4.1.3 | Category |  | Edit main category |  | Kamali | 45 min | 2024-12-28 | 2024-12-28 | Done
4.1.4 | Category |  | Delete main category |  | Kamali | 40 min | 2024-12-28 | 2024-12-28 | Done
4.1.5 | Category | Sub category | View Sub category |  | Kamali | 45 min | 2024-12-28 | 2024-12-28 | Done
4.1.6 | Category |  | Add sub category |  | Kamali | 40 min | 2024-12-28 | 2024-12-28 | Done
4.1.7 | Category |  | Edit Sub category |  | Kamali | 45 min | 2024-12-30 | 2024-12-30 | Done
4.1.8 | Category |  | Delete Sub category |  | Kamali | 45 min | 2024-12-30 | 2024-12-30 | Done
4.1.9 | Category | BOTH | Client-side Validations |  | Kamali | 40 min | 2024-12-30 | 2024-12-30 | Done
4.1.10 | Category |  | Rest API integration |  | Kamali | 40 min | 2024-12-30 | 2024-12-30 | Done
4.1.11 | Category |  | Unit Testing |  | Kamali | 30 min | 2024-12-30 | 2024-12-30 | Done
4.2 | Category | Server |  |  | Sujata | 90min | 2024-12-30 | 2024-12-30 | Done
4.2.1 | Category | Main Category | API-view main category |  | Sujata | 45min | 2024-12-30 | 2024-12-30 | Done
4.2.2 | Category |  | API-ADD main category |  | Sujata | 45min | 2024-12-30 | 2024-12-30 | Done
4.2.3 | Category |  | API- Edit main category |  | Sujata | 30min | 2024-12-30 | 2024-12-30 | Done
4.2.4 | Category |  | API- Delete main category |  | Sujata | 30min | 2024-12-30 | 2024-12-30 | Done
4.2.5 | Category | Sub category | API- view sub category |  | Sujata | 45min | 2024-12-30 | 2024-12-30 | Done
4.2.6 | Category |  | API - add sub category |  | Sujata | 45min | 2024-12-30 | 2024-12-30 | Done
4.2.7 | Category |  | API- Edit SUB category |  | Sujata | 30min | 2024-12-30 | 2024-12-30 | Done
4.2.8 | Category |  | API - Delete sub category |  | Sujata | 30min | 2024-12-30 | 2024-12-30 | Done
4.2.9 | Category |  | Server-side validation |  | Sujata | 20min | 2024-12-30 | 2024-12-30 | Done
4.2.10 | Category |  | Unit Testing |  | Sujata | 20min | 2024-12-30 | 2024-12-30 | Done
4.3 | Category | Database |  |  | Sujata | 40min | 2024-12-30 | 2024-12-30 | Done
4.3.1 | Category |  | Table creation |  | Sujata | 70min | 2024-12-30 | 2024-12-30 | Done
5 | Products | GUI/SERVER/DB |  |  | Kamali | 380 min | 2024-12-31 | 2024-12-31 | Done
5.1 | Products | GUI Creation |  |  | Kamali | 75 min | 2024-12-31 | 2024-12-31 | Done
5.1.1 | Products |  | ADD product |  | Kamali | 45 min | 2024-12-31 | 2024-12-31 | Done
5.1.2 | Products |  | view product |  | Kamali | 45 min | 2024-12-31 | 2024-12-31 | Done
5.1.3 | Products |  | edit product |  | Kamali | 45 min | 2024-12-31 | 2024-12-31 | Done
5.1.4 | Products |  | delete product |  | Kamali | 40 min | 2024-12-31 | 2024-12-31 | Done
5.1.5 | Products |  | Client-side Validations |  | Kamali | 45 min | 2024-12-31 | 2024-12-31 | Done
5.1.6 | Products |  | Rest API integration |  | Kamali | 40 min | 2024-12-31 | 2024-12-31 | Done
5.1.7 | Products |  | Unit Testing |  | Kamali | 45 min | 2024-12-31 | 2024-12-31 | Done
5.2 | Products | Server |  |  | Sujata | 250min | 2024-12-31 | 2024-12-31 | Done
5.2.1 | Products |  | API - add product |  | Sujata | 60min | 2024-12-31 | 2024-12-31 | Done
5.2.2 | Products |  | API - view product |  | Sujata | 30min | 2024-12-31 | 2024-12-31 | Done
5.2.3 | Products |  | API - delete product |  | Sujata | 30min | 2024-12-31 | 2024-12-31 | Done
5.2.4 | Products |  | API - edit product |  | Sujata | 40min | 2024-12-31 | 2024-12-31 | Done
5.2.5 | Products |  | Server-side validation |  | Sujata | 50min | 2024-12-31 | 2024-12-31 | Done
5.2.6 | Products |  | Unit Testing |  | Sujata | 40min | 2024-12-31 | 2024-12-31 | Done
5.3 | Products | Database |  |  | Sujata | 40min | 2024-12-31 | 2024-12-31 | Done
5.3.1 | Products |  | Table creation |  | Sujata | 30min | 2024-12-31 | 2024-12-31 | Done
6 | Order | GUI/SERVER/DB |  |  | Kamali | 385 min | 2025-01-02 | 2025-01-02 | Done
6.1 | Order | GUI Creation |  |  | Kamali | 75 min | 2025-01-02 | 2025-01-02 | Done
6.1.1 | Order |  | order list |  | Kamali | 45 min | 2025-01-02 | 2025-01-02 | Done
6.1.2 | Order |  | edit order |  | Kamali | 45 min | 2025-01-02 | 2025-01-02 | Done
6.1.3 | Order |  | track order |  | Kamali | 90 min | 2025-01-02 | 2025-01-02 | Done
6.1.4 | Order |  | Client-side Validations |  | Kamali | 50 min | 2025-01-02 | 2025-01-02 | Done
6.1.5 | Order |  | Rest API integration |  | Kamali | 40 min | 2025-01-02 | 2025-01-02 | Done
6.1.6 | Order |  | Unit Testing |  | Kamali | 40 min | 2025-01-02 | 2025-01-02 | Done
6.2 | Order | Server |  |  | Sujata | 250min | 2--01-2025 | 2025-01-02 | Done
6.2.1 | Order |  | Api-orderlist |  | Sujata | 75min | 2--01-2025 | 2--01-2025 | Done
6.2.2 | Order |  | Api-updateorder |  | Sujata | 60min | 2--01-2025 | 2--01-2025 | Done
6.2.3 | Order |  | Server-side validation |  | Sujata | 45min | 2--01-2025 | 2--01-2025 | Done
6.2.4 | Order |  | Unit Testing |  | Sujata | 30min | 2--01-2025 | 2--01-2025 | Done
6.3 | Order | Database |  |  | Sujata | 60min | 2--01-2025 | 2--01-2025 | Done
6.3.1 | Order |  | Table creation |  | Sujata | 45min | 2--01-2025 | 2--01-2025 | Done
7 | Users | GUI/SERVER/DB |  |  | Kamali | 410 min | 2025-01-02 | 2025-01-02 | Done
7.1 | Users | GUI Creation |  |  | Kamali | 75 min | 2025-01-02 | 2025-01-02 | Done
7.1.1 | Users |  | add user |  | Kamali | 50 min | 2025-01-02 | 2025-01-02 | Done
7.1.2 | Users |  | view user |  | Kamali | 50min | 2025-01-02 | 2025-01-02 | Done
7.1.3 | Users |  | edit user |  | Kamali | 45 min | 2025-01-02 | 2025-01-02 | Done
7.1.4 | Users |  | delete user |  | Kamali | 50 min | 2025-01-02 | 2025-01-02 | Done
7.1.5 | Users |  | Client-side Validations |  | Kamali | 50 min | 2025-01-02 | 2025-01-02 | Done
7.1.6 | Users |  | Rest API integration |  | Kamali | 50 min | 2025-01-02 | 2025-01-02 | Done
7.1.7 | Users |  | Unit Testing |  | Kamali | 40 min | 2025-01-02 | 2025-01-02 | Done
7.2 | Users | Server |  |  | Sujata | 200min | 2025-01-02 | 2025-01-02 | Done
7.2.1 | Users |  | Api - add user |  | Sujata | 45min | 2025-01-02 | 2025-01-02 | Done
7.2.2 | Users |  | Api -view user |  | Sujata | 30min | 2025-01-02 | 2025-01-02 | Done
7.2.3 | Users |  | Api -edit user |  | Sujata | 35min | 2025-01-02 | 2025-01-02 | Done
7.2.4 | Users |  | Api -delete user |  | Sujata | 30min | 2025-01-02 | 2025-01-02 | Done
7.2.5 | Users |  | Server-side validation |  | Sujata | 45min | 2025-01-02 | 2025-01-02 | Done
7.2.6 | Users |  | Unit Testing |  | Sujata | 30min | 2025-01-02 | 2025-01-02 | Done
7.3 | Users | Database |  |  | Sujata | 30min | 2025-01-02 | 2025-01-02 | Done
7.3.1 | Users |  | Table creation |  | Sujata | 30min | 2025-01-02 | 2025-01-02 | Done
8 | Roles | GUI/SERVER/DB |  |  | Kamali | 365 min | 2025-01-03 | 2025-01-03 | Done
8.1.1 | Roles | GUI Creation | delete roles |  | Kamali | 90min | 2025-01-03 | 2025-01-03 | Done
8.1.2 | Roles |  | view roles |  | Kamali | 40 min | 2025-01-03 | 2025-01-03 | Done
8.1.3 | Roles |  | create role |  | Kamali | 45 min | 2025-01-03 | 2025-01-03 | Done
8.1.4 | Roles |  | edit role |  | Kamali | 50 min | 2025-01-03 | 2025-01-03 | Done
8.1.5 | Roles |  | Client-side Validations |  | Kamali | 45min | 2025-01-03 | 2025-01-03 | Done
8.1.6 | Roles |  | Rest API integration |  | Kamali | 50 min | 2025-01-03 | 2025-01-03 | Done
8.1.7 | Roles |  | Unit Testing |  | Kamali | 45 min | 2025-01-03 | 2025-01-03 | Done
8.2.1 | Roles | Server | Api-view roles |  | Sujata | 100min | 2025-01-03 | 2025-01-03 | Done
8.2.2 | Roles |  | Api-edit roles |  | Sujata | 30min | 2025-01-03 | 2025-01-03 | Done
8.2.3 | Roles |  | Api-delete roles |  | Sujata | 20min | 2025-01-03 | 2025-01-03 | Done
8.2.4 | Roles |  | Api- create roles |  | Sujata | 45min | 2025-01-03 | 2025-01-03 | Done
8.2.5 | Roles |  | Server-side validation |  | Sujata | 30min | 2025-01-03 | 2025-01-03 | Done
8.2.6 | Roles |  | Unit Testing |  | Sujata | 30min | 2025-01-03 | 2025-01-03 | Done
8.3 | Roles | Database |  |  | Sujata | 30min | 2025-01-03 | 2025-01-03 | Done
8.3.1 | Roles |  | Table creation |  | Sujata | 35min | 2025-01-03 | 2025-01-03 | Done
9 | Profile | GUI/SERVER/DB |  |  | Kamali | 310 min | 2025-01-03 | 2025-01-03 | Done
9.1 | Profile | GUI Creation |  |  | Kamali | 75 min | 2025-01-03 | 2025-01-03 | Done
9.1.1 | Profile |  | get user details |  | Kamali | 50 min | 2025-01-03 | 2025-01-03 | Done
9.1.2 | Profile |  | update user |  | Kamali | 45 min | 2025-01-03 | 2025-01-03 | Done
9.1.3 | Profile |  | Client-side Validations |  | Kamali | 45 min | 2025-01-03 | 2025-01-03 | Done
9.1.4 | Profile |  | Rest API integration |  | Kamali | 50 min | 2025-01-03 | 2025-01-03 | Done
9.1.5 | Profile |  | Unit Testing |  | Kamali | 45 min | 2025-01-03 | 2025-01-03 | Done
9.2 | Profile | Server |  |  | Sujata | 75min | 2025-01-03 | 2025-01-03 | Done
9.2.1 | Profile |  | Api-get user |  | Sujata | 45min | 2025-01-03 | 2025-01-03 | Done
9.2.2 | Profile |  | Api-update user |  | Sujata | 30min | 2025-01-03 | 2025-01-03 | Done
9.2.3 | Profile |  | Server-side validation |  | Sujata | 30min | 2025-01-03 | 2025-01-03 | Done
9.2.4 | Profile |  | Unit Testing |  | Sujata | 30min | 2025-01-03 | 2025-01-03 | Done
9.3 | Profile | Database |  |  | Sujata | 40min | 2025-01-03 | 2025-01-03 | Done
9.3.1 | Profile |  | Table creation |  | Sujata | 40min | 2025-01-03 | 2025-01-03 | Done

## USER-ECOM
SL.NO | MODULES | TASKS | SUB-TASKS | MODIFICATION | ASSIGN | Effort min's | Start Date | End Date | STATUS | REMARKS
1 | Login | GUI/SERVER/DB |  |  | Kamali | 220 min | 2025-01-04 | 2025-01-04 | Done
1.1 | Login | GUI Creation |  |  | Kamali | 75 min | 2025-01-04 | 2025-01-04 | Done
1.1.1 | Login |  | Building user interface |  | Kamali | 50 min | 2025-01-04 | 2025-01-04 | Done
1.1.2 | Login |  | Client-side Validations |  | Kamali | 45 min | 2025-01-04 | 2025-01-04 | Done
1.1.3 | Login |  | Rest API integration |  | Kamali | 50 min | 2025-01-04 | 2025-01-04 | Done
1.1.4 | Login |  | Unit Testing |  | sujata | 30min | 2025-01-04 | 2025-01-04 | Done
1.2 | Login | Server |  |  | Sujata | 40min | 2025-01-04 | 2025-01-04 | Done
1.2.1 | Login |  | Server-side validation |  | Sujata | 30min | 2025-01-04 | 2025-01-04 | Done
1.2.2 | Login |  | Verify/Confirm login credentials |  | Sujata | 20min | 2025-01-04 | 2025-01-04 | Done
1.2.3 | Login |  | Unit Testing |  |  | 15min | 2025-01-04 | 2025-01-04 | Done
1.3 | Login | Database |  |  | Sujata | 20min | 2025-01-04 | 2025-01-04 | Done
1.3.1 | Login |  | Table creation |  | Sujata | 20min | 2025-01-04 | 2025-01-04 | Done
2 | Register | GUI/SERVER/DB |  |  | Kamali | 285 min | 2025-01-04 | 2025-01-04 | Done
2.1 | Register | GUI Creation |  |  | Kamali | 75 min | 2025-01-04 | 2025-01-04 | Done
2.1.1 | Register |  | Building user interface |  | Kamali | 50 min | 2025-01-04 | 2025-01-04 | Done
2.1.2 | Register |  | Client-side Validations |  | Kamali | 50 min | 2025-01-04 | 2025-01-04 | Done
2.1.3 | Register |  | Rest API integration |  | Kamali | 50 min | 2025-01-04 | 2025-01-04 | Done
2.1.4 | Register |  | Unit Testing |  | Kamali | 60 min | 2025-01-04 | 2025-01-04 | Done
2.2 | Register | Server |  |  | Sujata | 30min | 2025-01-04 | 2025-01-04 | Done
2.2.1 | Register |  | Server-side validation |  | Sujata | 20min | 2025-01-04 | 2025-01-04 | Done
2.2.2 | Register |  | Verify/Confirm Registration credentials |  | Sujata | 15min | 2025-01-04 | 2025-01-04 | Done
2.2.3 | Register |  | Unit Testing |  | Sujata | 20min | 2025-01-04 | 2025-01-04 | Done
2.3 | Register | Database |  |  | Sujata | 30min | 2025-01-04 | 2025-01-04 | Done
2.3.1 | Register |  | Table creation |  | Sujata | 20min | 2025-01-04 | 2025-01-04 | Done
3 | Forgot password | GUI/SERVER/DB |  |  | Kamali | 260 min | 2025-01-06 | 2025-01-06 | Done
3.1.1 | Forgot password | GUI Creation |  |  | Kamali | 80 min | 2025-01-06 | 2025-01-06 | Done
3.1.2 | Forgot password |  | Building user interface |  | Kamali | 60 min | 2025-01-06 | 2025-01-06 | Done
3.1.3 | Forgot password |  | Client-side Validations |  | Kamali | 50 min | 2025-01-06 | 2025-01-06 | Done
3.1.4 | Forgot password |  | Rest API integration |  | Kamali | 40 min | 2025-01-06 | 2025-01-06 | Done
3.1.5 | Forgot password |  | Unit Testing |  | Kamali | 30 min | 2025-01-06 | 2025-01-06 | Done
3.2 | Forgot password | Server |  |  | Sujata | 15min | 2025-01-06 | 2025-01-06 | Done
3.2.1 | Forgot password |  | Server-side validation |  | Sujata | 30min | 2025-01-06 | 2025-01-06 | Done
3.2.2 | Forgot password |  | Verify/Confirm Registration credentials |  | Sujata | 20min | 2025-01-06 | 2025-01-06 | Done
3.2.3 | Forgot password |  | Unit Testing |  | Sujata | 20min | 2025-01-06 | 2025-01-06 | Done
3.3 | Forgot password | Database |  |  | Sujata | 20min | 2025-01-06 | 2025-01-06 | Done
3.3.1 | Forgot password |  | Table creation |  | Sujata | 20min | 2025-01-06 | 2025-01-06 | Done
4 | Components | GUI/SERVER/DB |  |  | Kamali | 230 min | 2025-01-06 | 2025-01-06 | Done
4.1.1 | Components | GUI Creation |  |  | Kamali | 60 min | 2025-01-06 | 2025-01-06 | Done
4.1.2 | Components |  | Header |  | Kamali | 50 min | 2025-01-06 | 2025-01-06 | Done
4.1.3 | Components |  | Sidebar |  | Kamali | 50 min | 2025-01-06 | 2025-01-06 | Done
4.1.4 | Components |  | Footer |  | Kamali | 70 min | 2025-01-06 | 2025-01-06 | Done
5 | Home page | GUI/SERVER/DB |  |  | Kamali | 430 min | 2025-01-07 | 2025-01-07 | Done
5.1 | Home page | GUI Creation |  |  | Kamali | 70 min | 2025-01-07 | 2025-01-07 | Done
5.1.1 | Home page |  | view category |  | Kamali | 60 min | 2025-01-07 | 2025-01-07 | Done
5.1.2 | Home page |  | view product |  | Kamali | 45 min | 2025-01-07 | 2025-01-07 | Done
5.1.3 | Home page |  | search |  | Kamali | 50 min | 2025-01-07 | 2025-01-07 | Done
5.1.4 | Home page |  | add to cart |  | Kamali | 45 min | 2025-01-07 | 2025-01-07 | Done
5.1.5 | Home page |  | Client-side Validations |  | Kamali | 50 min | 2025-01-07 | 2025-01-07 | Done
5.1.6 | Home page |  | Rest API integration |  | Kamali | 70 min | 2025-01-07 | 2025-01-07 | Done
5.1.7 | Home page |  | Unit Testing |  | Kamali | 40 min | 2025-01-07 | 2025-01-07 | Done
5.2 | Home page | Server |  |  | Sujata | 40min | 2025-01-07 | 2025-01-07 | Done
5.2.1 | Home page |  | API-get category |  | Sujata | 30min | 2025-01-07 | 2025-01-07 | Done
5.2.2 | Home page |  | API-get product |  | Sujata | 20min | 2025-01-07 | 2025-01-07 | Done
5.2.3 | Home page |  | API-search |  | Sujata | 20min | 2025-01-07 | 2025-01-07 | Done
5.2.4 | Home page |  | API-add to cart |  | Sujata | 40min | 2025-01-07 | 2025-01-07 | Done
5.2.5 | Home page |  | Server-side validation |  | Sujata | 20min | 2025-01-07 | 2025-01-07 | Done
5.2.6 | Home page |  | Unit Testing |  | Sujata | 20min | 2025-01-07 | 2025-01-07 | Done
5.3 | Home page | Database |  |  | Sujata | 30min | 2025-01-07 | 2025-01-07 | Done
5.3.1 | Home page |  | Table creation |  | Sujata | 20min | 2025-01-07 | 2025-01-07 | Done
6 | Category page | GUI/SERVER/DB |  |  | Kamali | 350 min | 2025-01-07 | 2025-01-07 | Done
6.1 | Category page | GUI Creation |  |  | Kamali | 75 min | 2025-01-07 | 2025-01-07 | Done
6.1.1 | Category page |  | view sub category |  | Kamali | 45 min | 2025-01-07 | 2025-01-07 | Done
6.1.2 | Category page |  | view product |  | Kamali | 50 min | 2025-01-07 | 2025-01-07 | Done
6.1.3 | Category page |  | add to cart |  | Kamali | 45 min | 2025-01-07 | 2025-01-07 | Done
6.1.4 | Category page |  | Client-side Validations |  | Kamali | 40 min | 2025-01-07 | 2025-01-07 | Done
6.1.5 | Category page |  | Rest API integration |  | Kamali | 50 min | 2025-01-07 | 2025-01-07 | Done
6.1.6 | Category page |  | Unit Testing |  | Kamali | 45 min | 2025-01-07 | 2025-01-07 | Done
6.2 | Category page | Server |  |  | Sujata | 30min | 2025-01-07 | 2025-01-07 | Done
6.2.1 | Category page |  | api-view subcategory |  | Sujata | 30min | 2025-01-07 | 2025-01-07 | Done
6.2.2 | Category page |  | Server-side validation |  | Sujata | 20min | 2025-01-07 | 2025-01-07 | Done
6.2.3 | Category page |  | Unit Testing |  | Sujata | 20min | 2025-01-07 | 2025-01-07 | Done
6.3 | Category page | Database |  |  | Sujata | 30min | 2025-01-07 | 2025-01-07 | Done
6.3.1 | Category page |  | Table creation |  | Sujata | 20min | 2025-01-07 | 2025-01-07 | Done
7 | Product page | GUI/SERVER/DB |  |  | Kamali | 340 min | 2025-01-07 | 2025-01-08 | Done
7.1 | Product page | GUI Creation |  |  | Kamali | 75 min | 2025-01-07 | 2025-01-07 | Done
7.1.1 | Product page |  | view product |  | Kamali | 50 min | 2025-01-08 | 2025-01-08 | Done
7.1.2 | Product page |  | add to cart |  | Kamali | 50 min | 2025-01-08 | 2025-01-08 | Done
7.1.3 | Product page |  | Client-side Validations |  | Kamali | 75 min | 2025-01-08 | 2025-01-08 | Done
7.1.4 | Product page |  | Rest API integration |  | Kamali | 50 min | 2025-01-08 | 2025-01-08 | Done
7.1.5 | Product page |  | Unit Testing |  | Kamali | 40 min | 2025-01-08 | 2025-01-08 | Done
7.2 | Product page | Server |  |  | Sujata | 120min | 2025-01-08 | 2025-01-08 | Done
7.2.1 | Product page |  | API-view product |  | Sujata | 30min | 2025-01-08 | 2025-01-08 | Done
7.2.2 | Product page |  | API-add to cart |  | Sujata | 120min | 2025-01-08 | 2025-01-08 | Done
7.2.3 | Product page |  | Server-side validation |  | Sujata | 30min | 2025-01-08 | 2025-01-08 | Done
7.2.4 | Product page |  | Unit Testing |  | Sujata | 20min | 2025-01-08 | 2025-01-08 | Done
7.3 | Product page | Database |  |  | Sujata | 30min | 2025-01-08 | 2025-01-08 | Done
7.3.1 | Product page |  | Table creation |  | Sujata | 30min | 2025-01-08 | 2025-01-08 | Done
8 | Orders | GUI/SERVER/DB |  |  | Kamali | 395 min | 2025-01-08 | 2025-01-08 | Done
8.1 | Orders | GUI Creation |  |  | Kamali | 80 min | 2025-01-08 | 2025-01-08 | Done
8.1.1 | Orders |  | get all orders |  | Kamali | 75 min | 2025-01-08 | 2025-01-08 | Done
8.1.2 | Orders |  | order details |  | Kamali | 60 min | 2025-01-08 | 2025-01-08 | Done
8.1.3 | Orders |  | track order |  | Kamali | 45 min | 2025-01-08 | 2025-01-08 | Done
8.1.4 | Orders |  | Client-side Validations |  | Kamali | 40 min | 2025-01-08 | 2025-01-08 | Done
8.1.5 | Orders |  | Rest API integration |  | Kamali | 50 min | 2025-01-08 | 2025-01-08 | Done
8.1.6 | Orders |  | Unit Testing |  | Kamali | 45 min | 2025-01-08 | 2025-01-08 | Done
8.2 | Orders | Server |  |  | Sujata | 150min | 2025-01-08 | 2025-01-08 | Done
8.2.1 | Orders |  | API-get all orders |  | Sujata | 40min | 2025-01-08 | 2025-01-08 | Done
8.2.2 | Orders |  | Server-side validation |  | Sujata | 30min | 2025-01-08 | 2025-01-08 | Done
8.2.3 | Orders |  | Unit Testing |  | Sujata | 30min | 2025-01-08 | 2025-01-08 | Done
8.3 | Orders | Database |  |  | Sujata | 40min | 2025-01-08 | 2025-01-08 | Done
8.3.1 | Orders |  | Table creation |  | Sujata | 40min | 2025-01-08 | 2025-01-08 | Done
9 | Cart | GUI/SERVER/DB |  |  | Kamali | 425 min | 2025-01-09 | 2025-01-09 | Done
9.1 | Cart | GUI Creation |  |  | Kamali | 75 min | 2025-01-09 | 2025-01-09 | Done
9.1.1 | Cart |  | get cart |  | Kamali | 80 min | 2025-01-09 | 2025-01-09 | Done
9.1.2 | Cart |  | remove cart |  | Kamali | 75 min | 2025-01-09 | 2025-01-09 | Done
9.1.3 | Cart |  | place order |  | Kamali | 60 min | 2025-01-09 | 2025-01-09 | Done
9.1.4 | Cart |  | Client-side Validations |  | Kamali | 45 min | 2025-01-09 | 2025-01-09 | Done
9.1.5 | Cart |  | Rest API integration |  | Kamali | 40 min | 2025-01-09 | 2025-01-09 | Done
9.1.6 | Cart |  | Unit Testing |  | Kamali | 50 min | 2025-01-09 | 2025-01-09 | Done
9.2 | Cart | Server |  |  | Sujata | 140min | 2025-01-09 | 2025-01-09 | Done
9.2.1 | Cart |  | API-GET CART |  | Sujata | 50min | 2025-01-09 | 2025-01-09 | Done
9.2.2 | Cart |  | API- remove cart |  | Sujata | 45min | 2025-01-09 | 2025-01-09 | Done
9.2.3 | Cart |  | API-place order |  | Sujata | 35min | 2025-01-09 | 2025-01-09 | Done
9.2.4 | Cart |  | Server-side validation |  | Sujata | 20min | 2025-01-09 | 2025-01-09 | Done
9.2.5 | Cart |  | Unit Testing |  | Sujata | 20min | 2025-01-09 | 2025-01-09 | Done
9.3 | Cart | Database |  |  | Sujata | 35min | 2025-01-09 | 2025-01-09 | Done
9.3.1 | Cart |  | Table creation |  | Sujata | 34min | 2025-01-09 | 2025-01-09 | Done
10 | Profile | GUI/SERVER/DB |  |  | Kamali | 375 min | 2025-01-10 | 2025-01-10 | Done
10.1 | Profile | GUI Creation |  |  | Kamali | 75 min | 2025-01-10 | 2025-01-10 | Done
10.1.1 | Profile |  | get user details |  | Kamali | 80 min | 2025-01-10 | 2025-01-10 | Done
10.1.2 | Profile |  | update user |  | Kamali | 75 min | 2025-01-10 | 2025-01-10 | Done
10.1.3 | Profile |  | Client-side Validations |  | Kamali | 60 min | 2025-01-10 | 2025-01-10 | Done
10.1.4 | Profile |  | Rest API integration |  | Kamali | 45 min | 2025-01-10 | 2025-01-10 | Done
10.1.5 | Profile |  | Unit Testing |  | Kamali | 40 min | 2025-01-10 | 2025-01-10 | Done
10.2 | Profile | Server |  |  | Sujata | 60min | 2025-01-10 | 2025-01-10 | Done
10.2.1 | Profile |  | Api-get user |  | Sujata | 35min | 2025-01-10 | 2025-01-10 | Done
10.2.2 | Profile |  | Api-update user |  | Sujata | 30min | 2025-01-10 | 2025-01-10 | Done
10.2.3 | Profile |  | Server-side validation |  | Sujata | 30min | 2025-01-10 | 2025-01-10 | Done
10.2.4 | Profile |  | Unit Testing |  | Sujata | 20min | 2025-01-10 | 2025-01-10 | Done
10.3 | Profile | Database |  |  | Sujata | 45min | 2025-01-10 | 2025-01-10 | Done
10.3.1 | Profile |  | Table creation |  | Sujata | 30min | 2025-01-10 | 2025-01-10 | Done